## original
升级对象 | Function lost | Lost duration | 是否影响vNF业务 | 是否存在兼容性问题 | 需提前备份什么 | 升级失败恢复时间 | 建议采取的最佳升级方式
1.控制节点软件模块
控制节点OS | 单节点上所有服务 | 120s | No | No | ？ | ？ | 系统HA部署，升级备用，成功后倒换
Pacemaker等集群软件 | 集群备份功能 | 几分钟 | No | No |  |  | 先升级备后升级主，也可以在升级主时，先设置维护模式，然后在升级HA软件
Openstack MQ | 使用该MQ的所有Openstack模块.在HA情况下也会丢消息（我们现在做的是冷备份）；在集群方式下能做到不丢消息 | <5s |  |  | peizhi |  | 在集群方式下，逐个升级
Openstack DB(MySQL等) | 影响管理节点访问数据库，也就影响计算节上虚拟机添加删除等操作 | 几分钟 |  |  | peizhi |  | 先升级备后升级主
Openstack DB Data | 表结构升级几乎不影响功能 | 几秒 |  | 表设计要做到兼容
Openstack 无状态模块(各模块API等) | 该模块提供的服务 |  |  | 消息接口要兼容 |  |  | 用负载均衡的方式，逐个升级
Openstack 有状态模块(例如 Nova scheduler) | 该模块提供的服务 |  |  | 消息接口要兼容 |  |  | 主备方式，先升备再升主。（但一般都是冷备份，所以，升级时，会丢数据）
ODL升级(待细化) | 新业务无法接入 | [5 empty] | 集群方式逐个升级
2.计算节点软件升级
hostOS | 节点所有虚机down | 300 | Yes |  | config |  | fencing，immigrate all VMs
KVM/Qemu | 节点所有虚机down | <5s | Yes | 与Libvirt，agent |  |  | fencing，immigrate all VMs
Libvirt | manage ment |  | No | 与agent，Qemu等
openstack 各模块agent | 不影响虚拟机运行，但影响虚拟机的迁移等操作 |  |  | 大版本升级与控制节点可能存在兼容性
3.网络节点升级
L2 agent | 不影响（我们现在还没实现） | 几秒钟 | Yes | No | 无 | ？ | 先将虚拟机迁移到其它节点，再进行升级
L3 agent | 不影响（我们现在还没实现） | 几秒钟 | Yes | No | 无 | ？ | 无
OVS | 虚拟网络中断 | 几分钟 | Yes | No | 无 | ？ | 先将虚拟机迁移到其它节点，再进行升级
SR-IOV驱动 | 虚拟网络中断 | 几分钟 | Yes | No | 无 | ？ | 需要要先将虚机迁移到其它节点，再进行升级，如果不迁移，在升级前必须把虚拟机关机，把nova-compute服务停掉
4.存储节点升级
ceph升级 | 存储读取 | [5 empty] | 集群逐个升级

## English
Upload Target | Function lost | Lost duration | If vNF func lost | compatibility | Backup | Restore | requirement to avoid func lost
1.Software in control nodes
Control nodes OS | All function in the node, may affect other nodes | 300s | No | No | Config data of all software | re-install node from deployment server 10Min | HA deployment is required. Upgrade Standby nodes than switch-over
Cluster controller like Pacemaker | Monitoring func | 120s | No | No | config data local log | re-install 10Min | Set to maintain mode Upgrade standby node then switch-over
Openstack MQ | Message lost | <5s | No | No | config data local log | re-install 10Min | Active-Standby mode : upgrade standby node cluster mode: upgrade one by one
Openstack DB(MySQL etc.) | data access | 30s | No | No | config data local log | re-install 10Min | HA deployment is required. Upgrade Standby nodes than switch-over
Openstack DB Data | data access failure if uncompatible | 10s | No | data schema must meet backward-compatible | whole database | 1min
Openstack stateless module | capacity lower | 0s | No | interface internal or external | config data local log | re-install 5Min | upgrade one by one
Openstack stateful module | management operations | 10s | No | interface internal or external | config data local log | re-install 5Min | HA deployment is required. Upgrade Standby nodes than switch-over
ODL
2.compute nodes
hostOS | all VMs down in nodes | 300 | Yes | No | config data local log | re-install with deployment tools 10 Min | fencing，immigrate all VMs
KVM/Qemu | all VMs down in nodes | <5s | Yes | Interface with Libvert | config data | re-install with deployment tools 10 Min | fencing，immigrate all VMs
Libvirt | operation on VMs inside the node |  | No | Interface with KVM/Qemu | config data | re-install with deployment tools 10 Min
openstack agents | operation on VMs inside the node |  |  | Interface with control nodes | config data local log | re-install with deployment tools 10 Min
3.network nodes
L2 agent | operation on vswitch inside the node | 5s | No | Interface with control nodes | config data | re-install 5 Min
L3 agent | operation on vRouter inside the node | 5s | No | Interface with control nodes | config data | re-install 5 Min
OVS | network down | 60s | Yes | Interface with agent | config data local log | re-install with deployment tools 10 Min | fencing，immigrate all VMs
SR-IOV driver | network down | 300s | Yes | Interface with agent | config data | re-install 5 Min | fencing，immigrate all VMs
4.storage nodes
ceph