## Highlevel Plan
Dependencies |  | - DPDK - CollectD
WW = Work Week
DPDK
Week | … | X-11 | X-10 | X-9 | X-8 | X-7 | X-6 | X-5 | X-4 | X-3 | X-2 | X-1 | X
| … | WW37 | WW38 | WW39 | WW40 | WW41 | WW42 | WW43 | WW45 | WW46 | WW47 | WW48 | WW49
| Patches for the new release are developed and submitted to the mailing list. Features to be developed include: DPDK Keepalive, DPDK extended stats features and CollectD plugin for DPDK statistics | WW41: Community review, testing and rework of patches. No new patches submitted during this time. Patches without open issues applied; WW45: Testing of Release Candidate 1 and subsequent RCs. Bug Fixing; WW48: Testing of final RC. Only fixes to high priority bugs accepted during this time
[5 empty] | Final Version of all patches submitted to mailing list for review |  |  | Final Verision of all patches applied, RC1 built |  |  | Final RC built |  | Release available: DPDK Keepalive and DPDK extended stats features are part of DPDK 2.2
Additional RCs as Required
CollectD release Schedule is unknown, There doesn't seem to be a standard release cadence. Plan is to have collectD DPDK plugin pushed to github/upstreamed by the end of October
Note on F10: Tahhan, Maryam: DPDK Keepalive, DPDK extended stats features patches
End of November 2015
Mid November 2015
Mid/End October 2015
End of Sept 2015

## Reqs Traceability Matrix
DPDK Keep Alive
Deliverable | Reference | Description | Design | Functional Requirement |  |  |  |  | Performance Requirement
|  |  |  | Runs on the Host | Runs on the Guest | Configurable Timeouts | Measuring Detection time | Notifies a fault management entity
DPDK Keep Alive Sample App on Guest | JIRA ONP-348 | Development activity to support detection of ‘failed’ DPDK cores and notification to a HA/SA middleware. The purpose is to detect Packet Processing Core fails (e.g. infinite loop) and ensure the failure of the core does not result in a fault that is not detectable by a management entity. Detection of infinite loops is usually part of liveliness control in OpenSAF. |  | DPDK 2.2 | DPDK 2.2 | DPDK 2.2 | DPDK 2.2 | DPDK 2.2 | Doesn't impact performance
DPDK Stats Extensions
Deliverable | Reference | Description | Design | Functional Requirement |  |  |  | Performance Requirement
|  |  |  | Expose Error Registers to DPDK Sample Apps | Expose VF Registers to DPDK Sample Apps | Extend Exposed registers to include those not in struct hw_stats | Extend Exposed registers to include Sums that are not in struct hw_stats
IXGBE error/extended stats Exposure |  |  |  | X | DPDK 2.2 | DPDK 2.2 | DPDK 2.2 | Doesn't impact performance
i40e error/extended stats Exposure |  |  |  | DPDK 2.2 | DPDK 2.2 | DPDK 2.2 | DPDK 2.2
Sample App that retrieves Stats on the Host |  |  |  | X | N/A | N/A | N/A
Sample App that retrieves Host Stats on the Guest |  |  |  | N/A | N/A |  | N/A
CollectD DPDK stats Plugin |  | CollectD Plugin that runs on the host and polls stats from DPDK |  | DPDK 2.2 |  |  |  | Doesn't impact performance
X = Done
Note on I3: Tahhan, Maryam: Hook Function to be filled in by whoever