## Highlevel Plan
Dependencies |  | None, project is self contained
WW = Work Week
VSPERF
Week | … | X-11 | X-10 | X-9 | X-8 | X-7 | X-6 | X-5 | X-4 | X-3 | X-2 | X-1 | X
| … | WW37 | WW38 | WW39 | WW40 | WW41 | WW42 | WW43 | WW45 | WW46 | WW47 | WW48 | WW49
| Patches for the new release are developed and submitted to the mailing list. Features to be developed include: See the Backlog tab, anything with the Rel B tag will be included in release B. Any other stories that are complete in time will also make it into the release. |  |  |  |  | Community review, testing and rework of patches. No new patches submitted during this time. Patches without open issues applied |  |  | Testing of Release Candidate 1 and subsequent RCs. Bug Fixing |  |  | Testing of final RC. Only fixes to high priority bugs accepted during this time
[5 empty] | Final Version of all patches submitted to mailing list for review |  |  | Final Verision of all patches applied, RC1 built |  |  | Final RC built |  | Release available
Additional RCs as Required
Note on F10: Tahhan, Maryam:
End of November 2015
Mid November 2015
Mid/End October 2015
End of Sept 2015

## Backlog
Project | Release | Summary | Issue Type | Status | Assignee | Reporter | Creator | Description
VSPERF |  | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases | Epic | In Progress | Tahhan, Maryam | Tahhan, Maryam | Tahhan, Maryam | TOIT is an Apache licensed test framework that was developed in Python to enable integration testing of Open vSwitch (OVS), and in particular the netdev-dpdk bridge in OVS. TOIT was adopted for the the “Characterize vSwitch Performance for Telco NFV Use Cases” OPNFV project (VSPERF). The main goal of VSPERF is to develop a generic and architecture agnostic vSwitch testing framework and associated tests that will serve as a basis for validating the suitability of different vSwitch implementations in Telco NFV environments. TOIT was extended as a starting point to help achieve the project goal. However, TOIT’s current format is not generic enough to cater for different vSwitches and does not meet the agreed upon directory structure of the VSPERF project in OPNFV, thus TOIT needs to be redesigned to be more generic and to allow it to fit into the predefined repository structure. Definition of Done: * VSPERF design is approved by the OPNFV community * VSPERF design is implemented and upstreamed to the OPNFV community with the tests that we are able to implement (there are limitations regarding the tests we can implement based on the IXIA licenses that are available to us). * VSPERF outputs a complete benchmarking report based on the set of tests that are run.
Project | Release | Summary | Issue Type | Status | Assignee | Reporter | Creator | Description | Epic Link | Sprint | Story Points
VSPERF | Rel B | Tech debt - Affinitize vswitch threads for Vanilla OVS | Story | In Progress | Giller, Robin | Tahhan, Maryam | Tahhan, Maryam | Currently in VSPERF the threads for the vswitch are not affinitized to any cores. As an end user I would like to be able to set the thread affinities for my vswitch threads through settings/ test-params and for vsperf to affinitize the threads to the selected core/s. The affinitization scheme that should be followed is specified in https://01.org/sites/default/files/page/intel_onp_server_release_1.3.1_benchmark_test_report.pdf Section: 4.3 Core Usage for OVS... a similar affinitization to what we use for OVS DPDK should be used DoD End user can select the thread affinity for vswitch threads through the cli or settings and the vswitch module looks after the thread affinitization | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases | Sprint 12 | 1
VSPERF | Rel B | Tech debt - Affinitize vswitch threads for OVS - DPDK | Story | In Progress | Giller, Robin | Tahhan, Maryam | Tahhan, Maryam | Currently in VSPERF the threads for the vswitch are not affinitized to any cores. As an end user I would like to be able to set the thread affinities for my vswitch threads through settings/ test-params and for vsperf to affinitize the threads to the selected core/s. The affinitization scheme that should be followed is specified in https://01.org/sites/default/files/page/intel_onp_server_release_1.3.1_benchmark_test_report.pdf Section: 4.3 Core Usage for OVS DoD End user can select the thread affinity for vswitch threads through the cli or settings and the vswitch module looks after the thread affinitization | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases | Sprint 12 | 2
VSPERF | Rel B | Convert Documentation to RST format and follow the layout setout by opnfv_documentation | Story | In Progress | Tahhan, Maryam | Tahhan, Maryam | Tahhan, Maryam | Convert VSPERF documentation from Markdown to ReSTructured text and ensure that it follows the format: gerrit.opnfv.org/<project> l-- docs/ l l-- some-project-description.rst l l-- other-doc-1.rst l l-- images/ l l-- *.png¦*.jpg l-- release/ l l-- some-release-doc.rst l l-- images/ l l-- *.png¦*.jpg l-- requirements/ l l-- requirements.rst l l-- images/ l l-- *.png¦*.jpg l-- design_docs/ l l-- some-design-doc.rst l l-- images/ l l-- *.png¦*.jpg l-- some_project_file.py l-- some_shell_script.sh l-- INFO `-- README Reference: https://wiki.opnfv.org/documentation_projects/opnfv_documentation?s[]=documentation | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases | Sprint 12 | 1
VSPERF | Rel B | Default config picks up OVS variants from 'make' | Story | Open | Tahhan, Maryam | O Mahony, Billy | O Mahony, Billy | Pre-req: ONP-1975 This possibly only requires changes to the std configuration files. And some testing :) DOD: Once vswitchperf/src/make has been run. Running a test with vanilla-ovs, vhost-user-ovs, vhost-cuse-ovs, .... does not require any building or configuration changes - the vswitch needs only to specified on the command line. | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases |  | 2
VSPERF | Rel B | 'make' creates all required variants of vSwitch | Story | Open | Tahhan, Maryam | O Mahony, Billy | O Mahony, Billy | Currently the VSPERF makefiles make just one variant of vSwitch - OVS with DPDK-vhost-user. To make the other variants the makefile has to be edited. And the make re-run. We need to have the makefile build all required versions: * Vanilla OVS * DPDK-vhost-user OVS * DPDK-vhost-cuse OVS * IVSHMEM? The build system should *not* checkout several versions of the src - as that will make the build slow (which will also affect the jenkins ci commit gate on opnfv gerrit). Just one version of both dpdk and ovs src. Furthermore the build system currently edits the config/common_linux config file in checked out to src/dpdk/dpdk. This causes complications as src/dpdk/dpdk is exported and built in the guest OS for scenarios involving VMs and the guest OS need a pristine version of the dpdk src's to build - a modified one can cause build failures when the guest tries to build dpdk. It's a separate story to make changes to VSPERFs code and/or standard configuration so that it picks up the various OVS variants automatically. DOD: Doing vsperf/src$ make a) creates all the required OVS variants. b) provides a pristine copy of the dpdk src | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases |  | 3
VSPERF | Rel B | Fix derived performance figures | Story | Open | Giller, Robin | O Mahony, Billy | O Mahony, Billy | Since vsperf (ixnet trafficgen) started using AggResults.csv to pull out traffic results after bi-dir support was added. Some of the derived results are wrong (derived meaning these are figures vsperf calculates from the info available in the raw ixnet results). For example here for perf/continuous the tx_fps is lower than the rx_fps: ... throughput_tx_fps, Value: 6439197. ... throughput_rx_fps, Value: 13525168.014 ... h3. Further Analysis Clearly all we can get from AggregateResults.csv is: Tx Rate (% Line Rate) Rx Throughput (% Line Rate) Rx Throughput (fps) <Ignore latency figures - not to be an issue> Given that: * some tests (vlan frame mod) may change the packet sizes as they pass through the DUT * some tests involved packet loss (simple perf test (MaxFowardingRate) - NOTE forwarding rate (lossy) is different to throughput (lossless). Is there any more of the currently reported results fields: * throughput_tx_fps, * throughput_rx_fps, * throughput_tx_mbps, * throughput_rx_mbps, * throughput_tx_percent, * throughput_rx_percent, that we can calculate? (I don't think so). What if we look at using the other results .csv files? Where the traffic is broken down by input/output. Can we 'fill-in-the-blanks' then? h3. Tasks * Establish what results we can correctly derive from only AggResults.csv * Estimate the effort required to implement code to derive or extract all the currently stated results - this will require parsing additional .csv files from ixnet. * Decide what extra figures if any are required and implement the derivation/extraction of these. DOD * All results from ixnet traffic generator are correct in all cases for all tests - bidi, unidir, frame modification * Code is upstreamed to opnfv | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases | Sprint #11, Sprint 12 | 4
VSPERF | Rel B | Tech debt - Affinitize vswitch threads for Vanilla OVS | Story | In Progress | Giller, Robin | Tahhan, Maryam | Tahhan, Maryam | Currently in VSPERF the threads for the vswitch are not affinitized to any cores. As an end user I would like to be able to set the thread affinities for my vswitch threads through settings/ test-params and for vsperf to affinitize the threads to the selected core/s. The affinitization scheme that should be followed is specified in https://01.org/sites/default/files/page/intel_onp_server_release_1.3.1_benchmark_test_report.pdf Section: 4.3 Core Usage for OVS... a similar affinitization to what we use for OVS DPDK should be used DoD End user can select the thread affinity for vswitch threads through the cli or settings and the vswitch module looks after the thread affinitization | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases | Sprint 12 | 1
VSPERF | Rel B | Tech debt - Affinitize vswitch threads for OVS - DPDK | Story | In Progress | Giller, Robin | Tahhan, Maryam | Tahhan, Maryam | Currently in VSPERF the threads for the vswitch are not affinitized to any cores. As an end user I would like to be able to set the thread affinities for my vswitch threads through settings/ test-params and for vsperf to affinitize the threads to the selected core/s. The affinitization scheme that should be followed is specified in https://01.org/sites/default/files/page/intel_onp_server_release_1.3.1_benchmark_test_report.pdf Section: 4.3 Core Usage for OVS DoD End user can select the thread affinity for vswitch threads through the cli or settings and the vswitch module looks after the thread affinitization | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases | Sprint 12 | 2
VSPERF | Rel B | Convert Documentation to RST format and follow the layout setout by opnfv_documentation | Story | In Progress | Tahhan, Maryam | Tahhan, Maryam | Tahhan, Maryam | Convert VSPERF documentation from Markdown to ReSTructured text and ensure that it follows the format: gerrit.opnfv.org/<project> l-- docs/ l l-- some-project-description.rst l l-- other-doc-1.rst l l-- images/ l l-- *.png¦*.jpg l-- release/ l l-- some-release-doc.rst l l-- images/ l l-- *.png¦*.jpg l-- requirements/ l l-- requirements.rst l l-- images/ l l-- *.png¦*.jpg l-- design_docs/ l l-- some-design-doc.rst l l-- images/ l l-- *.png¦*.jpg l-- some_project_file.py l-- some_shell_script.sh l-- INFO `-- README Reference: https://wiki.opnfv.org/documentation_projects/opnfv_documentation?s[]=documentation | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases | Sprint 12 | 1
VSPERF | Rel B | Default config picks up OVS variants from 'make' | Story | Open | Tahhan, Maryam | O Mahony, Billy | O Mahony, Billy | Pre-req: ONP-1975 This possibly only requires changes to the std configuration files. And some testing :) DOD: Once vswitchperf/src/make has been run. Running a test with vanilla-ovs, vhost-user-ovs, vhost-cuse-ovs, .... does not require any building or configuration changes - the vswitch needs only to specified on the command line. | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases |  | 2
VSPERF | Rel B | 'make' creates all required variants of vSwitch | Story | Open | Tahhan, Maryam | O Mahony, Billy | O Mahony, Billy | Currently the VSPERF makefiles make just one variant of vSwitch - OVS with DPDK-vhost-user. To make the other variants the makefile has to be edited. And the make re-run. We need to have the makefile build all required versions: * Vanilla OVS * DPDK-vhost-user OVS * DPDK-vhost-cuse OVS * IVSHMEM? The build system should *not* checkout several versions of the src - as that will make the build slow (which will also affect the jenkins ci commit gate on opnfv gerrit). Just one version of both dpdk and ovs src. Furthermore the build system currently edits the config/common_linux config file in checked out to src/dpdk/dpdk. This causes complications as src/dpdk/dpdk is exported and built in the guest OS for scenarios involving VMs and the guest OS need a pristine version of the dpdk src's to build - a modified one can cause build failures when the guest tries to build dpdk. It's a separate story to make changes to VSPERFs code and/or standard configuration so that it picks up the various OVS variants automatically. DOD: Doing vsperf/src$ make a) creates all the required OVS variants. b) provides a pristine copy of the dpdk src | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases |  | 3
VSPERF | Rel B | Fix derived performance figures | Story | Open | Giller, Robin | O Mahony, Billy | O Mahony, Billy | Since vsperf (ixnet trafficgen) started using AggResults.csv to pull out traffic results after bi-dir support was added. Some of the derived results are wrong (derived meaning these are figures vsperf calculates from the info available in the raw ixnet results). For example here for perf/continuous the tx_fps is lower than the rx_fps: ... throughput_tx_fps, Value: 6439197. ... throughput_rx_fps, Value: 13525168.014 ... h3. Further Analysis Clearly all we can get from AggregateResults.csv is: Tx Rate (% Line Rate) Rx Throughput (% Line Rate) Rx Throughput (fps) <Ignore latency figures - not to be an issue> Given that: * some tests (vlan frame mod) may change the packet sizes as they pass through the DUT * some tests involved packet loss (simple perf test (MaxFowardingRate) - NOTE forwarding rate (lossy) is different to throughput (lossless). Is there any more of the currently reported results fields: * throughput_tx_fps, * throughput_rx_fps, * throughput_tx_mbps, * throughput_rx_mbps, * throughput_tx_percent, * throughput_rx_percent, that we can calculate? (I don't think so). What if we look at using the other results .csv files? Where the traffic is broken down by input/output. Can we 'fill-in-the-blanks' then? h3. Tasks * Establish what results we can correctly derive from only AggResults.csv * Estimate the effort required to implement code to derive or extract all the currently stated results - this will require parsing additional .csv files from ixnet. * Decide what extra figures if any are required and implement the derivation/extraction of these. DOD * All results from ixnet traffic generator are correct in all cases for all tests - bidi, unidir, frame modification * Code is upstreamed to opnfv | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases | Sprint #11, Sprint 12 | 4
VSPERF | Rel B | Enable Bidi - for B2B P2P test | Story | Open | Lynch, Michael A | Tahhan, Maryam | Tahhan, Maryam | Enable the bidirectional traffic feature for the Back to Back traffic implementation | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases |  | 2
VSPERF | Rel B | Enable PVVP - vhost cuse | Story | Open | Lynch, Michael A | Tahhan, Maryam | Tahhan, Maryam | Implement infrastructure to allow for VM loopback (PVVP) with vhost-cuse as the guest access method, this involves: * Implementing the appropriate interpretation of the deployment scenario in the vswitch directory - adding 2 phy ports, adding 4 vhost-cuse ports and setting up the appropriate flows. * Implementing the appropriate interpretation of the deployment scenario in the vnf directory - launching qemu with the appropriate parameters * Affinitization of vswitchd and vnf threads for the best known performance configuration. * Running all the tests (throughput, b2b) with the deployment scenarios. * Update/create any necessary docuementation. * Update News.md * Pushing patches to Gerrit for Review * Reworking patches. * Upstreaming patches to VSPERF repository. D.O.D Patches meet all the requirements listed above and are upstreamed to OPNFV community | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases |  | 3
VSPERF | Rel B | Enable PVVP - vhost user | Story | Open | Lynch, Michael A | Tahhan, Maryam | Tahhan, Maryam | Implement infrastructure to allow for VM2VM loopback (PVVP) with vhost-user as the guest access method, this involved: * Allowing vhostuser to be a configuration option for the vswtich and vnf that overrides vhost-cuse (if not enabled by the vhost user PVP story) * Enable building vhost-user in the src directory as a new target (if not enabled by the vhost user PVP story) * Implementing the appropriate interpretation of the deployment scenario in the vswitch directory - adding 2 phy ports, adding 4 vhost-user ports and setting up the appropriate flows. * Implementing the appropriate interpretation of the deployment scenario in the vnf directory - launching qemu with the appropriate parameters * Affinitization of vswitchd and vnf threads for the best known performance configuration. * Running all the tests (throughput, b2b) with the deployment scenarios. * Update any relevant documentation/create documentation * Update News.md * Pushing patches to Gerrit for Review * Reworking patches. * Upstreaming patches to VSPERF repository. D.O.D Patches meet all the requirements listed above and are upstreamed to OPNFV community | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases
VSPERF | Rel B | Bidirectional IxNetwork Test - PVVP Vanilla OVS | Story | Open | Lynch, Michael A | Tahhan, Maryam | Tahhan, Maryam | Enable Bidirectional flows for Vanilla OVS PVVP. Modify both the switch flows and the vnf forwarding rules (if necessary to enable this) | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases |  | 2
VSPERF | Rel B | Bidirectional IxNetwork Test - PVP Vanilla OVS | Story | Open | Lynch, Michael A | Tahhan, Maryam | Tahhan, Maryam | Enable Bidirectional flows for Vanilla OVS PVP. Modify both the switch flows and the vnf forwarding rules (if necessary to enable this) | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases |  | 2
VSPERF | Rel B | Bidirectional IxNetwork Test - PVVP OVS-DPDK | Story | Open | Lynch, Michael A | Tahhan, Maryam | Tahhan, Maryam | Enable Bidirectional flows for OVS-DPDK PVVP. Modify both the switch flows and the vnf forwarding rules (if necessary to enable this) | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases |  | 2
VSPERF | Rel B | Bidirectional IxNetwork Test - PVP OVS-DPDK vhost user | Story | Open | Giller, Robin | Tahhan, Maryam | Tahhan, Maryam | Enable Bidirectional flows for OVS-DPDK PVP. Modify both the switch flows and the vnf forwarding rules (if necessary to enable this) | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases |  | 2
VSPERF | Rel B | Enable memory utilization metric collection for RFC 2544 tests | Story | Open | Giller, Robin | Tahhan, Maryam | Tahhan, Maryam | This story is closely coupled with 1504, 1767, 1768 & 1769. vSwitch resource utilization should includes any related process (such as ovsdb) but not any VMs. | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases |  | 2
VSPERF | Rel B | Enable CPU utilization metric collection for RFC2544 tests. | Story | Open | Tahhan, Maryam | Tahhan, Maryam | Tahhan, Maryam | This story is closely coupled with 1504, 1767, 1768 & 1769. In fact I think it's totally covered by other stories. Suggest delete? | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases |  | 2
VSPERF | Rel B | Option for different num of pmds | Story | Open | Tahhan, Maryam | Tahhan, Maryam | Tahhan, Maryam | ToDo | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases |  | 2
VSPERF | Rel B | Implement infrastructure to enable Vanilla OVS vSwitch PVP | Story | Open | Giller, Robin | Tahhan, Maryam | Tahhan, Maryam | Implement infrastructure to allow for VM loopback (PVP) with virtio-net (TAP device) as the guest access method, this involves: * Implementing the appropriate interpretation of the deployment scenarios scenario in the vswitch directory - adding 2 phy ports, adding 2 virtio-net ports and setting up the appropriate flows . * Implementing the appropriate interpretation of the deployment scenario in the vnf directory - launching qemu with the appropriate parameters * Run Affinitization of vswitchd and vnf threads for the best known performance configuration. * Running all the tests (throughput, b2b) with the deployment scenario. * Update any documentation/create new documentation if necessary. * update News.md * Push Pushing patches to Gerrit for Review * Rework Reworking patches. * Upstream Upstreaming patches to VSPERF repository. D.O.D Patches meet all the requirements listed above and are upstreamed to OPNFV community | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases |  | 5
VSPERF | Rel B | Update HLD after the VSPERF implementation | Story | Open | Tahhan, Maryam | Tahhan, Maryam | Tahhan, Maryam | This story will ensure that all people that have worked on re-implementing TOIT and have/are moving off to another project update the HLD sections for the components they implemented. This story should be assigned to: Timo, Michal and Meghan. D.O.D: HLD up to date with the latest implementation | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases |  | 2
VSPERF | Rel B | Update Sysmetrics implementation | Story | Open | Giller, Robin | Tahhan, Maryam | Tahhan, Maryam | Currently sysmetrics collects the CPU usage for the entire system for a particular time interval. To collect accurate CPU metrics for vSwitch tests, we need to implement functions that will allow us to collect CPU metrics for a particular process and over the lifetime of the test. The recommended utility to use is pidstat This Task involves: * Investigate an appropriate utility to collect CPU metrics that we can use (pidstat...) * integrate that utility under sysmetrics in vsperf. * test * push patches for internal review * rework patches * push patches to OPNFV community * rework patches The stats we want to collect are: * %CPU : Total percentage of CPU time used by the task - using pidstat. * %Mem - using pidstat. * minflt/s: Total number of minor faults the task has made per second, those which have not required loading a memory page from disk.- using pidstat. * majflt/s: Total number of major faults the task has made per second, those which have required loading a memory page from disk.- using pidstat. * VSZ: Virtual Size: The virtual memory usage of entire task in kilobytes.- using pidstat. * RSS: Resident Set Size: The non-swapped physical memory used by the task in kilobytes.- using pidstat. D.O.D: Patches are upstreamed to OPNFV community | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases |  | 5
VSPERF | Rel B | Extend VSPERF Benchmarking Report | Story | Open | Giller, Robin | O Mahony, Billy | O Mahony, Billy | In the previous implementation of TOIT only RFC2544 throughput tests generate results to a .md document. This implementation needs to be ported to VSPERF and the results from other tests need to be added to the report. i.e. one report for all tests that were run. There is a bunch of information related to the system and tests that can affect the repeatability of a test and should be recorded: * Platform details: CPU, memory, # of enabled cores and # of cores used for the test. * OS version (for host and VNF), kernel version (for host and VNF), GRUB boot parameters (for host and VNF) and platform BIOS settings. * Selected vSwitch, version # or commit id used. * vSwitch launch command line if it’s been parameterised. * Memory allocation to the vSwitch – which NUMA node it’s using, how many memory channels… * DPDK or any other SW dependency version # or commit id used. * Memory allocation to a VM - if it's from Hugpages/elsewhere. * VM storage type: snapshot/independent persistent/ independent non-persistent. * # of phy NICs, versions, type and the PCI slot they are plugged into. * NIC interrupt configuration. * # of VMs, hypervisor, and version of the hypervisor. * # of Virtual NICs, versions, type and driver. * # of virtual CPUs and their core affinity on the host. * # vNIC interrupt configuration. * Test duration. * # of flows. * Thread affinitization for the applications on the host. Thought and consideration needs to be given to the implementation regarding: How to support more tests? How to modify report when only a subset of test results have been run? | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases |  | 8
VSPERF | Rel B | Enable PVP - vhost cuse | Story | In Progress | Giller, Robin | Tahhan, Maryam | Tahhan, Maryam | Implement infrastructure to allow for VM loopback (PVP) with vhost-cuse as the guest access method, this involves: * Inserting the eventfd kernel module * launching the vswitch with any additional required parameters for vhost-cuse * Implementing the appropriate interpretation of the deployment scenario in the vswitch directory - adding 2 phy ports, adding 2 vhost-cuse ports and setting up the appropriate flows. * Implementing the appropriate interpretation of the deployment scenario in the vnf directory - launching qemu with the appropriate parameters * Affinitization of vswitchd and vnf threads for the best known performance configuration. * Running all the tests (throughput, b2b) with the deployment scenarios. * Update/create any necessary docuementation. * Update News.md * Pushing patches to Gerrit for Review * Reworking patches. * Upstreaming patches to VSPERF repository. D.O.D Patches meet all the requirements listed above and are upstreamed to OPNFV community | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases |  | 5
VSPERF | Rel B | vhost toit: qemu versions | Story | Open | Giller, Robin | Kavanagh, Mark B | Kavanagh, Mark B | == Acceptance Criteria == == Tasks == - Add support for multiple versions of qemu (cmd line params would be different) == Notes == Different port types require different versions of QEMU: dpdkrports: patched 1.6.2 dpdkvhostports (cuse): 1.6.2 (or 2.1+ provided the cmd line parameters are changed like so https://git-ger-5.devtools.intel.com/gerrit/#/c/133321/) dpdkvhostuserports: 2.2 At the moment, for dpdkvhostuserport tests, the user must modify the QEMU_DIR varaible in the settings.py file to point to a build of QEMU 2.2 prior to running the test. This DoD of this story is for this not to be necessary, eg. to auto-set the QEMU_DIR to the necessary QEMU version depending on the port type used in the test being executed. | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases |  | 5
VSPERF |  | Enable IVSHMEM PVVP | Story | Open | Lynch, Michael A | Tahhan, Maryam | Tahhan, Maryam | Implement infrastructure to allow for VM2VM loopback (PVVP) with IVSHMEM as the guest access method, this involves: Implementing the appropriate interpretation of the deployment scenario in the vswitch directory - adding 2 phy ports, adding 4 IVSHMEM ports and setting up the appropriate flows. Implementing the appropriate interpretation of the deployment scenario in the vnf directory - launching qemu with the appropriate parameters Affinitization of vswitchd and vnf threads for the best known performance configuration. Running all the tests (throughput, b2b) with the deployment scenarios. Update any relevant documentation/create documentation Update News.md Pushing patches to Gerrit for Review Reworking patches. Upstreaming patches to VSPERF repository. D.O.D Patches meet all the requirements listed above and are upstreamed to OPNFV community | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases |  | 3
VSPERF |  | Enable IVSHMEM PVP | Story | Open | Lynch, Michael A | Tahhan, Maryam | Tahhan, Maryam | Implement infrastructure to allow for PVP with IVSHMEM as the guest access method, this involved: Allowing IVSHMEM to be a configuration option for the vswtich and vnf. Enable building cloning patched qemu and building it in the src directory as a new target. Implementing the appropriate interpretation of the deployment scenario in the vswitch directory - adding 2 phy ports, adding 2 IVSHMEM ports and setting up the appropriate flows. Implementing the appropriate interpretation of the deployment scenario in the vnf directory - launching qemu with the appropriate parameters Affinitization of vswitchd and vnf threads for the best known performance configuration. Running all the tests (throughput, b2b) with the deployment scenarios. Update any relevant documentation/create documentation Update News.md Pushing patches to Gerrit for Review Reworking patches. Upstreaming patches to VSPERF repository. D.O.D Patches meet all the requirements listed above and are upstreamed to OPNFV community | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases |  | 3
VSPERF |  | Enable VM-vswitch-VM - vhost user | Story | Open | Lynch, Michael A | Tahhan, Maryam | Tahhan, Maryam | Implement infrastructure to allow for VM-vswitch-VM with vhost-user as the guest access method, this involved: Implementing the appropriate interpretation of the deployment scenario in the vswitch directory - adding 4 vhost-user ports and setting up the appropriate flows. Implementing the appropriate interpretation of the deployment scenario in the vnf directory - launching qemu with the appropriate parameters Affinitization of vswitchd and vnf threads for the best known performance configuration. Running all the tests (throughput, b2b) with the deployment scenarios. Update any relevant documentation/create documentation Update News.md Pushing patches to Gerrit for Review Reworking patches. Upstreaming patches to VSPERF repository. D.O.D Patches meet all the requirements listed above and are upstreamed to OPNFV community | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases
VSPERF |  | Port LTD.CPDPCouplingPortAddition From old TOIT | Story | Open | Tahhan, Maryam | Tahhan, Maryam | Tahhan, Maryam | Ensure all the tests conform to the definition in the LTD when porting any tests. Port the previous implementation of this Test to VSPERF. This should be a patch from Chris Nolan in gerrit for the old TOIT repo. | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases |  | 2
VSPERF |  | Port LTD.CPDPCouplingFlowAddition from old TOIT | Story | Open | Tahhan, Maryam | Tahhan, Maryam | Tahhan, Maryam | Ensure all the tests conform to the definition in the LTD when porting any tests. Port the previous implementation of this Test to VSPERF. This should be a patch from Chris Nolan in gerrit for the old TOIT repo. | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases |  | 2
VSPERF |  | Port LTD.Memory.RFC2544.0PacketLoss from old TOIT | Story | Open | Tahhan, Maryam | Tahhan, Maryam | Tahhan, Maryam | Ensure all the tests conform to the definition in the LTD when porting any tests. Port the previous implementation of this Test to VSPERF. | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases |  | 2
VSPERF |  | Port LTD.Scalability.RFC2544.0PacketLoss from old TOIT | Story | Open | Tahhan, Maryam | Tahhan, Maryam | Tahhan, Maryam | Ensure all the tests conform to the definition in the LTD when porting any tests. Port the previous implementation of this Test to VSPERF. | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases |  | 2
VSPERF |  | Port LTD.Throughput.RFC2544.PacketLossRatioSoak from old TOIT | Story | Open | Tahhan, Maryam | Tahhan, Maryam | Tahhan, Maryam | Ensure all the tests conform to the definition in the LTD when porting any tests. Port the previous implementation of this Test to VSPERF. | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases |  | 2
VSPERF |  | Port LTD.Throughput.Fastpath from old TOIT | Story | Open | Tahhan, Maryam | Tahhan, Maryam | Tahhan, Maryam | Ensure all the tests conform to the definition in the LTD when porting any tests. Port the previous implementation of this Test to VSPERF. | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases |  | 2
VSPERF |  | Port LTD.Throughput.Slowpath from Old Toit | Story | Open | Tahhan, Maryam | Tahhan, Maryam | Tahhan, Maryam | Ensure all the tests conform to the definition in the LTD when porting any tests. Port the previous implementation of this Test to VSPERF. | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases |  | 2
VSPERF |  | port LTD.Scalability.RFC2544.ZeroPacketLoss from previous implementation in TOIT | Story | Open | Tahhan, Maryam | Tahhan, Maryam | Tahhan, Maryam | Ensure all the tests conform to the definition in the LTD when porting any tests. Port tests for LTD.Scalability.RFC2544.ZeroPacketLoss. Loopback: PHY-VM-PHY throughput RFC2544 scalability test. Phy2Phy: PHY-PHY throughput RFC2544 scalability test. VM2VM: PHY-VM-VM-PHY throughput RFC2544 scalability test. | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases |  | 2
VSPERF |  | Port memory.rfc2544.scalability from previous implementation in TOIT | Story | Open | Tahhan, Maryam | Tahhan, Maryam | Tahhan, Maryam | Ensure all the tests conform to the definition in the LTD when porting any tests. Port Tests for LTD.Memory.RFC2544.Scalability. Loopback: PHY-VM-PHY memory utilisation RFC2544 scalability test. Phy2Phy: PHY-PHY memory utilisation RFC2544 scalability test. VM2VM: PHY-VM-VM-PHY memory utilisation RFC2544 scalability test. | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases |  | 2
VSPERF |  | Port cpu_utilization.rfc2544.scalability from previous implementation in TOIT | Story | Open | Giller, Robin | Tahhan, Maryam | Tahhan, Maryam | This story is closely coupled with 1504, 1767, 1768 & 1769. vSwitch resource utilization should includes any related process (such as ovsdb) but not any VMs. Ensure all the tests conform to the definition in the LTD when porting any tests. Port tests for LTD.CPUUtilization.RFC2544.0PacketLoss. (NOTE: sysmetrics isn't suitable for our needs) Loopback: PHY-VM-PHY CPU utilisation RFC2544 scalability test. Phy2Phy: PHY-PHY memory utilisation RFC2544 scalability test. VM2VM: PHY-VM-VM-PHY CPU utilisation RFC2544 scalability test. | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases |  | 2
VSPERF |  | Port cpu.rfc2544.zero_packet_loss from previous implementation in TOIT | Story | Open | Tahhan, Maryam | Tahhan, Maryam | Tahhan, Maryam | Ensure all the tests conform to the definition in the LTD when porting any tests. Port Tests for LTD.CPU.RFC2544.ZeroPacketLoss: Loopback: PHY-VM-PHY CPU-stress RFC2544 zero packet loss test. Phy2Phy: PHY-PHY CPU-stress RFC2544 zero packet loss test. VM2VM: PHY-VM-VM-PHY CPU-stress RFC2544 zero packet loss test. | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases |  | 2
VSPERF |  | Enable/Integrate other traffic types (TCP, IMIX, RTP…) | Story | Open | Tahhan, Maryam | Tahhan, Maryam | Tahhan, Maryam | Todo | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases |  | 2
VSPERF |  | Flow Classification extension | Story | Open | O Mahony, Billy | Tahhan, Maryam | Tahhan, Maryam | Flow classification parameters for any vSwitch performance tests should be extended to include: the input port, the source IP address, the destination IP address and the Ethernet protocol type field. This involves extending the flow matching parameters in any rules installed on the vswitch (for all deployment scenarios) from just matching inport and outport to matching the fields specified above. | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases |  | 3
VSPERF |  | Implement LTD.Memory.RFC2544.0PacketLoss | Story | In Progress | Giller, Robin | O Mahony, Billy | O Mahony, Billy | -- presumably it's just "tput & latency with a memory intensive application on the same NUMA socket" but current text says ""Memory utilization of the system when a memory intensive application runs on the same socket" We need to find a stress application than can allow loading of memory is a well defined way. This story overlaps with 1520. * concentrate on the running of an arbitrary app with arbitrary configuration (cli args will be enough hopefully) in the background app - then new apps could be plugged in at will (e.g. for memory stressing, i/o stressing etc etc.) * configuration of this app needs to be added to the test config * then app needs to be started for the duration of the test. | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases |  | 3
VSPERF |  | Implement LTD.CPU.RFC2544.0PacketLoss | Story | In Progress | Giller, Robin | O Mahony, Billy | O Mahony, Billy | LTD.CPU.RFC2544.0PacketLoss -- presumably it's just "tput & latency with a cpu intensive load on the same NUMA socket" but current text says "CPU utilization of the system when a memory intensive application runs on the same socket" This story overlaps with 1521. We need to find a stress application than can allow loading of certain cores on certain numa nodes to a well defined amount of load. * concentrate on the running of an arbitrary app with arbitrary configuration (cli args will be enough hopefully) in the background app - then new apps could be plugged in at will (e.g. for memory stressing, i/o stressing etc etc.) * configuration of this app needs to be added to the test config * then app needs to be started for the duration of the test. | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases |  | 5
VSPERF |  | Implement LTD.CPDPCouplingPortAddition | Story | Open | Gray, Mark D | O Mahony, Billy | O Mahony, Billy | -- measure 0PacketLoss fwding rate in face of many port/high-rate-of-port-addition&removal (it's not clear which I'd suggest a test implementation that can do both - ie insert 100K ports and the add&remove 1K ports pers second while doing rfc2544 tput) | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases |  | 4
VSPERF |  | Implement LTD.CPDPCouplingFlowAddition | Story | Open | Giller, Robin | O Mahony, Billy | O Mahony, Billy | The vswitch LTD on OPNFV web site has updated the definition of this test recently and needs to be accepted before starting implementing this test (ww30 2015) measure 0PacketLoss fwding rate in face of many flows/high-rate-of-flow-addition&removal (it's not clear which I'd suggest a test implementation that can do both - ie insert 100K flows and the add&remove 1K flows pers second while doing rfc2544 tput) | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases |  | 3
VSPERF |  | LTD.Throughput.RFC2544.Soak | Story | Open | Tahhan, Maryam | O Mahony, Billy | O Mahony, Billy | The spec of this test has changed recently. https://gerrit.opnfv.org/gerrit/#/c/690/1/test_spec/vswitchperf_ltd.md This test requires the result of a previous test as input. Maryam has some code in toit repo on retrieving test results from previous tests. This code needs to be understood first. The test requires reporting all the 60s time intervals during the soak where packets were lost. This functionality does not exist in the current code base - we need to check internally and perhaps with Ixia on how to implement this. As a PlanB consider reporting the total packet loss for the duration of the soak. DOD - code merged to master on OPNFV repo | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases |  | 5
VSPERF |  | LTD.Scalability.RFC2544.0PacketLoss | Story | In Progress | Giller, Robin | O Mahony, Billy | O Mahony, Billy | The definition of this test has changed recently (https://gerrit.opnfv.org/gerrit/#/c/403/) This test can be acheived by adding a multistream config item, taking the required number of flows to setup in the traffic, to the existing testcase and then running the standard 2544 Throughput test. Ciara has already done this for IxNet - the config just needs to be plumbed through from the 01_testcase.conf via ITraffic to the IxNet. From Ciara: So far, I've extended the multistream capability in IxNetwork to allow the user to specify the number of flows to test with (rather than being limited to either 1 flow or 64,000 flows). The patch is here: https://git-ger-5.devtools.intel.com/gerrit/#/c/134573/ | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases |  | 3
VSPERF |  | LTD.Throughput.RFC2544.PacketLossRatioFrameModification | Story | In Progress | O Mahony, Billy | O Mahony, Billy | O Mahony, Billy | Support a test setting (in *any* entry in 01_testcases.conf) called FrameModification which can be set to one of frame modification types currently supported in toit. Adding this config line to any test should run the test with Frame modification turned on. DOD patch submitted to OPNFV. | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases |  | 8
VSPERF |  | Add Pylint & Tox to VSPERF commit gate | Story | Open | Giller, Robin | Halton, Meghan [X] | Halton, Meghan [X] | Pylint and Tox configuration and support were removed as part of the release to OPNFV. Add them back in. Integrate with VSPERF commit gate DoD: Can run pylint from tox with 0 reported errors. Any legitimate false positives should be resolved with the syntax specified in the contributing guide. | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases |  | 1
VSPERF |  | Add ability to use a "test spec" (list of tests to run) back into TOIT | Story | Ready | Giller, Robin | Halton, Meghan [X] | Halton, Meghan [X] | This feature is required for the nightly build/smoke testing etc. Have an external test-spec file which can be used to run a specific set of tests using ./vsperf. DoD: Run a list of tests specified through a test spec file, passed into the command line of vsperf. | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases |  | 1
VSPERF |  | Establish TOIT commit gate tests for VSPERF project | Story | Ready | Lynch, Michael A | Tahhan, Maryam | Tahhan, Maryam | Setup a commit gate Jenkins job with Octopus for the VSPERF project to run a minimal set of TOIT tests whenever patches are pushed to the VSPERF repository (under gerrit for review). D.O.D A basic set of TOIT tests run whenever patches are pushed to VSPERF, this will serve as a means of CI to make sure that new patches don't break any existing TOIT tests/code. | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases |  | 3
VSPERF |  | Benchmarking baseline performance of Open vSwitch | Story | Open | Barrett, Vinny | Gray, Mark D | Pandhyaram, RajeswariX [X] | Rationale • Basic benchmarking of open vSwitch without tuning Description • Run test cases • Produce a performance report for Open vSwitch characterization with a simple fwding workload • Produce a performance report for Open vSwitch characterization with a VNF workloads Key dependencies • Dependent on stories 1-3 Key assumptions: • Assume all tests automated and functionally working • Assume that no modifications to OVS are required • Opens • multi-core scalability is undefined | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases |  | 20
VSPERF |  | Integrating an open source VNF into test setup | Story | Open | Barrett, Vinny | Gray, Mark D | Pandhyaram, RajeswariX [X] | Rationale • Tests would need perform characterization of the vSwitch under the load of a real VNF Description • Document VNF configurations to be tested • Setup and configure VNFs • Run test cases manually • Automate setup of VNFs into test framework • Get all test cases running functionally with expected performance • Document setups Key dependencies • Open source VNF Key assumptions: • Intel DPPD will be used • Support will be available from Intel labs Belgium • Assume we can generate the types of traffic that are required for the VNF • Assume that other traffic generators may need to be used • Assume 10 VNF test cases in DPPD will be run – • Fallback would be 2 VNF’s – (5) • Remaining VNF testing (3) • Assume default configuration per VNF • Assume that DPPD VNF’s are compatible with OVS • Assume that no modifications to OVS are required • Opens • How would normal behavior of the VNF be simulated | Test framework for Characterize vSwitch Performance for Telco NFV Use Cases |  | 80